## How to use
attestqa planner
Source | AQ-05 Implementation Plan and Release Schedule v1.3 (10 Oct 2026). Planned hours are estimates from that document.
Capacity | 4–5 hours a day, 7 days a week, as stated by Vijay. Daily capacity is set once on the Settings sheet.
What to fill in | Only cells with blue text on a yellow background. Everything else is calculated.
Daily log | Each day: hours worked, the release it went to (filled automatically from the date), what you did, and whether the journal line was written.
Work items | When an item is done: actual hours and status. Status choices: Not started, In progress, Done, Moved.
Releases | Calculated: planned hours, hours logged in that cycle, capacity of the cycle, and the gap. Fill in the release status and the Zenodo DOI after release day.
Weeks | Calculated weekly totals against 31 hours, for a quick check every Sunday.
Example daily entry | Date 12 Oct 2026 · Hours 4.5 · What I did: 'Monorepo created; agentic-qa history imported with git subtree; f2771d4 resolves' · Journal: Yes
Rule from AQ-05 §6 | A release ships on the 15th with whatever is finished and tested. Unfinished work items are marked Moved and added to the next release.

## Releases
Release | Cycle starts | Release date | Headline | Days in cycle | Capacity h | Planned work h | Planned / capacity | Hours logged | Logged − planned | Items done | Items total | Status | Zenodo DOI
v1.0.0 | 2026-10-12 | 2026-11-15 | Major: engine and CLI: Jira/ADO stories to governed tests, any company model | 35 | 157.5 | 138 | 87.62% | 0 | -138 | 0 | 7 | Planned
v1.1.0 | 2026-11-16 | 2026-12-15 | Company sign-in, healing suggestions, Selenium import | 30 | 135 | 114 | 84.44% | 0 | -114 | 0 | 4 | Planned
v1.2.0 | 2026-12-16 | 2027-01-15 | First signed Windows app: Attest | 31 | 139.5 | 125 | 89.61% | 0 | -125 | 0 | 4 | Planned
v1.3.0 | 2027-01-16 | 2027-02-15 | Requirements and Specify in the app | 31 | 139.5 | 120 | 86.02% | 0 | -120 | 0 | 4 | Planned
v1.4.0 | 2027-02-16 | 2027-03-15 | Explore; web testing complete | 28 | 126 | 115 | 91.27% | 0 | -115 | 0 | 3 | Planned
v2.0.0 | 2027-03-16 | 2027-04-15 | Major: API testing | 31 | 139.5 | 110 | 78.85% | 0 | -110 | 0 | 4 | Planned
v2.1.0 | 2027-04-16 | 2027-05-15 | API Explore; contracts from traffic | 30 | 135 | 100 | 74.07% | 0 | -100 | 0 | 3 | Planned
v3.0.0 | 2027-05-16 | 2027-06-15 | Major: web version of attestqa | 31 | 139.5 | 105 | 75.27% | 0 | -105 | 0 | 3 | Planned
v3.1.0 | 2027-06-16 | 2027-07-15 | MCP and multi-user approvals | 30 | 135 | 100 | 74.07% | 0 | -100 | 0 | 3 | Planned
v4.0.0 | 2027-07-16 | 2027-08-15 | Major: security testing | 31 | 139.5 | 105 | 75.27% | 0 | -105 | 0 | 3 | Planned
v4.1.0 | 2027-08-16 | 2027-09-15 | Active scanning | 31 | 139.5 | 110 | 78.85% | 0 | -110 | 0 | 3 | Planned
v5.0.0 | 2027-09-16 | 2027-10-15 | Major: ETL testing; all four types | 30 | 135 | 110 | 81.48% | 0 | -110 | 0 | 4 | Planned
|  |  | Total |  | 1660.5 | 1352 | 81.42% | 0
Planned / capacity turns red above the share set on Settings (85%).

## Settings
Setting | Value | Note
Planned hours per day | 4.5 | Stated by Vijay: 4–5 hours a day, 7 days a week
Planned hours per week | 31.5 | Calculated
Share of capacity planned as work | 85% | AQ-05 §1: about 115 of 135 hours a month; the rest is slack

## Work items
Release | # | Work item | Planned h | Actual h | Status | Done on | Notes
v1.0.0 | 1 | Monorepo set-up, subtree import of agentic-qa, research log live | 15 |  | Not started
v1.0.0 | 2 | Publish attestqa 1.1.0 and the compatibility shim from the old repository | 3 |  | Not started
v1.0.0 | 3 | Engine 2.0: ledger additions, tool literal, replay tests over the Paper I corpus | 25 |  | Not started
v1.0.0 | 4 | Provider conformance suite, TokenSource, registerProvider, gateway | 20 |  | Not started
v1.0.0 | 5 | Tracker interface over the Azure DevOps MCP path; Jira adapter | 40 |  | Not started
v1.0.0 | 6 | Coverage tags and aqa coverage; report completeness | 25 |  | Not started
v1.0.0 | 7 | synthdata as a package; shared triage fixtures with pw-triage | 10 |  | Not started
v1.1.0 | 1 | AWS Bedrock provider; Entra ID and AWS SSO token sources | 37 |  | Not started
v1.1.0 | 2 | pw-self-heal in the heal role, suggest-only, with fixture test | 20 |  | Not started
v1.1.0 | 3 | aqa import selenium through sel2pw | 12 |  | Not started
v1.1.0 | 4 | Desktop groundwork: client interface, FakeClient, Electron skeleton | 45 |  | Not started
v1.2.0 | 1 | Attest screen and approval dialog | 45 |  | Not started
v1.2.0 | 2 | Worker process, credential vault, validated IPC | 25 |  | Not started
v1.2.0 | 3 | Headed Chromium; ledger question box | 20 |  | Not started
v1.2.0 | 4 | Renderer-secrets tests; code signing, installer, auto-update | 35 |  | Not started
v1.3.0 | 1 | First-run flow, provider round-trip test, site login | 30 |  | Not started
v1.3.0 | 2 | Requirements screen: ADO/Jira, query, coverage grid | 35 |  | Not started
v1.3.0 | 3 | Specify screen via bdd2pw and pw-emit; user_edit events | 45 |  | Not started
v1.3.0 | 4 | Selenium import entry in the app | 10 |  | Not started
v1.4.0 | 1 | Web Explore: skill, refusal rules, site map, drafts, rulings | 70 |  | Not started
v1.4.0 | 2 | App accessibility and end-to-end tests | 25 |  | Not started
v1.4.0 | 3 | User guide and demo video | 20 |  | Not started
v2.0.0 | 1 | pw-emit 1.4 with API, security and ETL nodes (pw-emit repo) | 20 |  | Not started
v2.0.0 | 2 | api adapter, api_hosts scope, three API refusal rules | 35 |  | Not started
v2.0.0 | 3 | API in Specify, Attest, coverage; type switch | 25 |  | Not started
v2.0.0 | 4 | API targets onboarded; study S2 cross-model runs | 30 |  | Not started
v2.1.0 | 1 | API Explore from OpenAPI or recorded traffic | 25 |  | Not started
v2.1.0 | 2 | usagecontract as second API oracle | 20 |  | Not started
v2.1.0 | 3 | Study S3 cross-site runs; hardening | 55 |  | Not started
v3.0.0 | 1 | @attestqa/server REST + live updates; HttpClient | 55 |  | Not started
v3.0.0 | 2 | OIDC sign-in and roles | 20 |  | Not started
v3.0.0 | 3 | Run queue and container workers | 30 |  | Not started
v3.1.0 | 1 | MCP endpoint (run_story, run_status, resources) | 30 |  | Not started
v3.1.0 | 2 | Container image and deployment guide | 25 |  | Not started
v3.1.0 | 3 | Multi-user approvals; server security review | 45 |  | Not started
v4.0.0 | 1 | Passive security checks in Playwright | 30 |  | Not started
v4.0.0 | 2 | adapter-zap: passive scan and spider | 35 |  | Not started
v4.0.0 | 3 | ASVS mapping; three security refusal rules; UI | 40 |  | Not started
v4.1.0 | 1 | Active scan behind authorisation; ZAP findings as results; S4 security | 45 |  | Not started
v4.1.0 | 2 | adapter-sql: read-only parser and connections (ships in v5.0.0) | 50 |  | Not started
v4.1.0 | 3 | Hardening | 15 |  | Not started
v5.0.0 | 1 | Mapping format; ETL Explore; three ETL refusal rules | 50 |  | Not started
v5.0.0 | 2 | Reference load with synthdata and seeded faults | 20 |  | Not started
v5.0.0 | 3 | ETL in the app; S4 ETL runs | 25 |  | Not started
v5.0.0 | 4 | First-year review and year-two roadmap | 15 |  | Not started
|  | Total | 1352 | 0

## Daily log
Date | Day | Release cycle | Hours | What I did | Journal written?
2026-10-12 | Mon | v1.0.0
2026-10-13 | Tue | v1.0.0
2026-10-14 | Wed | v1.0.0
2026-10-15 | Thu | v1.0.0
2026-10-16 | Fri | v1.0.0
2026-10-17 | Sat | v1.0.0
2026-10-18 | Sun | v1.0.0
2026-10-19 | Mon | v1.0.0
2026-10-20 | Tue | v1.0.0
2026-10-21 | Wed | v1.0.0
2026-10-22 | Thu | v1.0.0
2026-10-23 | Fri | v1.0.0
2026-10-24 | Sat | v1.0.0
2026-10-25 | Sun | v1.0.0
2026-10-26 | Mon | v1.0.0
2026-10-27 | Tue | v1.0.0
2026-10-28 | Wed | v1.0.0
2026-10-29 | Thu | v1.0.0
2026-10-30 | Fri | v1.0.0
2026-10-31 | Sat | v1.0.0
2026-11-01 | Sun | v1.0.0
2026-11-02 | Mon | v1.0.0
2026-11-03 | Tue | v1.0.0
2026-11-04 | Wed | v1.0.0
2026-11-05 | Thu | v1.0.0
2026-11-06 | Fri | v1.0.0
2026-11-07 | Sat | v1.0.0
2026-11-08 | Sun | v1.0.0
2026-11-09 | Mon | v1.0.0
2026-11-10 | Tue | v1.0.0
2026-11-11 | Wed | v1.0.0
2026-11-12 | Thu | v1.0.0
2026-11-13 | Fri | v1.0.0
2026-11-14 | Sat | v1.0.0
2026-11-15 | Sun | v1.0.0
2026-11-16 | Mon | v1.1.0
2026-11-17 | Tue | v1.1.0
2026-11-18 | Wed | v1.1.0
2026-11-19 | Thu | v1.1.0
2026-11-20 | Fri | v1.1.0
2026-11-21 | Sat | v1.1.0
2026-11-22 | Sun | v1.1.0
2026-11-23 | Mon | v1.1.0
2026-11-24 | Tue | v1.1.0
2026-11-25 | Wed | v1.1.0
2026-11-26 | Thu | v1.1.0
2026-11-27 | Fri | v1.1.0
2026-11-28 | Sat | v1.1.0
2026-11-29 | Sun | v1.1.0
2026-11-30 | Mon | v1.1.0
2026-12-01 | Tue | v1.1.0
2026-12-02 | Wed | v1.1.0
2026-12-03 | Thu | v1.1.0
2026-12-04 | Fri | v1.1.0
2026-12-05 | Sat | v1.1.0
2026-12-06 | Sun | v1.1.0
2026-12-07 | Mon | v1.1.0
2026-12-08 | Tue | v1.1.0
2026-12-09 | Wed | v1.1.0
2026-12-10 | Thu | v1.1.0
2026-12-11 | Fri | v1.1.0
2026-12-12 | Sat | v1.1.0
2026-12-13 | Sun | v1.1.0
2026-12-14 | Mon | v1.1.0
2026-12-15 | Tue | v1.1.0
2026-12-16 | Wed | v1.2.0
2026-12-17 | Thu | v1.2.0
2026-12-18 | Fri | v1.2.0
2026-12-19 | Sat | v1.2.0
2026-12-20 | Sun | v1.2.0
2026-12-21 | Mon | v1.2.0
2026-12-22 | Tue | v1.2.0
2026-12-23 | Wed | v1.2.0
2026-12-24 | Thu | v1.2.0
2026-12-25 | Fri | v1.2.0
2026-12-26 | Sat | v1.2.0
2026-12-27 | Sun | v1.2.0
2026-12-28 | Mon | v1.2.0
2026-12-29 | Tue | v1.2.0
2026-12-30 | Wed | v1.2.0
2026-12-31 | Thu | v1.2.0
2027-01-01 | Fri | v1.2.0
2027-01-02 | Sat | v1.2.0
2027-01-03 | Sun | v1.2.0
2027-01-04 | Mon | v1.2.0
2027-01-05 | Tue | v1.2.0
2027-01-06 | Wed | v1.2.0
2027-01-07 | Thu | v1.2.0
2027-01-08 | Fri | v1.2.0
2027-01-09 | Sat | v1.2.0
2027-01-10 | Sun | v1.2.0
2027-01-11 | Mon | v1.2.0
2027-01-12 | Tue | v1.2.0
2027-01-13 | Wed | v1.2.0
2027-01-14 | Thu | v1.2.0
2027-01-15 | Fri | v1.2.0
2027-01-16 | Sat | v1.3.0
2027-01-17 | Sun | v1.3.0
2027-01-18 | Mon | v1.3.0
2027-01-19 | Tue | v1.3.0
2027-01-20 | Wed | v1.3.0
2027-01-21 | Thu | v1.3.0
2027-01-22 | Fri | v1.3.0
2027-01-23 | Sat | v1.3.0
2027-01-24 | Sun | v1.3.0
2027-01-25 | Mon | v1.3.0
2027-01-26 | Tue | v1.3.0
2027-01-27 | Wed | v1.3.0
2027-01-28 | Thu | v1.3.0
2027-01-29 | Fri | v1.3.0
2027-01-30 | Sat | v1.3.0
2027-01-31 | Sun | v1.3.0
2027-02-01 | Mon | v1.3.0
2027-02-02 | Tue | v1.3.0
2027-02-03 | Wed | v1.3.0
2027-02-04 | Thu | v1.3.0
2027-02-05 | Fri | v1.3.0
2027-02-06 | Sat | v1.3.0
2027-02-07 | Sun | v1.3.0
2027-02-08 | Mon | v1.3.0
2027-02-09 | Tue | v1.3.0
2027-02-10 | Wed | v1.3.0
2027-02-11 | Thu | v1.3.0
2027-02-12 | Fri | v1.3.0
2027-02-13 | Sat | v1.3.0
2027-02-14 | Sun | v1.3.0
2027-02-15 | Mon | v1.3.0
2027-02-16 | Tue | v1.4.0
2027-02-17 | Wed | v1.4.0
2027-02-18 | Thu | v1.4.0
2027-02-19 | Fri | v1.4.0
2027-02-20 | Sat | v1.4.0
2027-02-21 | Sun | v1.4.0
2027-02-22 | Mon | v1.4.0
2027-02-23 | Tue | v1.4.0
2027-02-24 | Wed | v1.4.0
2027-02-25 | Thu | v1.4.0
2027-02-26 | Fri | v1.4.0
2027-02-27 | Sat | v1.4.0
2027-02-28 | Sun | v1.4.0
2027-03-01 | Mon | v1.4.0
2027-03-02 | Tue | v1.4.0
2027-03-03 | Wed | v1.4.0
2027-03-04 | Thu | v1.4.0
2027-03-05 | Fri | v1.4.0
2027-03-06 | Sat | v1.4.0
2027-03-07 | Sun | v1.4.0
2027-03-08 | Mon | v1.4.0
2027-03-09 | Tue | v1.4.0
2027-03-10 | Wed | v1.4.0
2027-03-11 | Thu | v1.4.0
2027-03-12 | Fri | v1.4.0
2027-03-13 | Sat | v1.4.0
2027-03-14 | Sun | v1.4.0
2027-03-15 | Mon | v1.4.0
2027-03-16 | Tue | v2.0.0
2027-03-17 | Wed | v2.0.0
2027-03-18 | Thu | v2.0.0
2027-03-19 | Fri | v2.0.0
2027-03-20 | Sat | v2.0.0
2027-03-21 | Sun | v2.0.0
2027-03-22 | Mon | v2.0.0
2027-03-23 | Tue | v2.0.0
2027-03-24 | Wed | v2.0.0
2027-03-25 | Thu | v2.0.0
2027-03-26 | Fri | v2.0.0
2027-03-27 | Sat | v2.0.0
2027-03-28 | Sun | v2.0.0
2027-03-29 | Mon | v2.0.0
2027-03-30 | Tue | v2.0.0
2027-03-31 | Wed | v2.0.0
2027-04-01 | Thu | v2.0.0
2027-04-02 | Fri | v2.0.0
2027-04-03 | Sat | v2.0.0
2027-04-04 | Sun | v2.0.0
2027-04-05 | Mon | v2.0.0
2027-04-06 | Tue | v2.0.0
2027-04-07 | Wed | v2.0.0
2027-04-08 | Thu | v2.0.0
2027-04-09 | Fri | v2.0.0
2027-04-10 | Sat | v2.0.0
2027-04-11 | Sun | v2.0.0
2027-04-12 | Mon | v2.0.0
2027-04-13 | Tue | v2.0.0
2027-04-14 | Wed | v2.0.0
2027-04-15 | Thu | v2.0.0
2027-04-16 | Fri | v2.1.0
2027-04-17 | Sat | v2.1.0
2027-04-18 | Sun | v2.1.0
2027-04-19 | Mon | v2.1.0
2027-04-20 | Tue | v2.1.0
2027-04-21 | Wed | v2.1.0
2027-04-22 | Thu | v2.1.0
2027-04-23 | Fri | v2.1.0
2027-04-24 | Sat | v2.1.0
2027-04-25 | Sun | v2.1.0
2027-04-26 | Mon | v2.1.0
2027-04-27 | Tue | v2.1.0
2027-04-28 | Wed | v2.1.0
2027-04-29 | Thu | v2.1.0
2027-04-30 | Fri | v2.1.0
2027-05-01 | Sat | v2.1.0
2027-05-02 | Sun | v2.1.0
2027-05-03 | Mon | v2.1.0
2027-05-04 | Tue | v2.1.0
2027-05-05 | Wed | v2.1.0
2027-05-06 | Thu | v2.1.0
2027-05-07 | Fri | v2.1.0
2027-05-08 | Sat | v2.1.0
2027-05-09 | Sun | v2.1.0
2027-05-10 | Mon | v2.1.0
2027-05-11 | Tue | v2.1.0
2027-05-12 | Wed | v2.1.0
2027-05-13 | Thu | v2.1.0
2027-05-14 | Fri | v2.1.0
2027-05-15 | Sat | v2.1.0
2027-05-16 | Sun | v3.0.0
2027-05-17 | Mon | v3.0.0
2027-05-18 | Tue | v3.0.0
2027-05-19 | Wed | v3.0.0
2027-05-20 | Thu | v3.0.0
2027-05-21 | Fri | v3.0.0
2027-05-22 | Sat | v3.0.0
2027-05-23 | Sun | v3.0.0
2027-05-24 | Mon | v3.0.0
2027-05-25 | Tue | v3.0.0
2027-05-26 | Wed | v3.0.0
2027-05-27 | Thu | v3.0.0
2027-05-28 | Fri | v3.0.0
2027-05-29 | Sat | v3.0.0
2027-05-30 | Sun | v3.0.0
2027-05-31 | Mon | v3.0.0
2027-06-01 | Tue | v3.0.0
2027-06-02 | Wed | v3.0.0
2027-06-03 | Thu | v3.0.0
2027-06-04 | Fri | v3.0.0
2027-06-05 | Sat | v3.0.0
2027-06-06 | Sun | v3.0.0
2027-06-07 | Mon | v3.0.0
2027-06-08 | Tue | v3.0.0
2027-06-09 | Wed | v3.0.0
2027-06-10 | Thu | v3.0.0
2027-06-11 | Fri | v3.0.0
2027-06-12 | Sat | v3.0.0
2027-06-13 | Sun | v3.0.0
2027-06-14 | Mon | v3.0.0
2027-06-15 | Tue | v3.0.0
2027-06-16 | Wed | v3.1.0
2027-06-17 | Thu | v3.1.0
2027-06-18 | Fri | v3.1.0
2027-06-19 | Sat | v3.1.0
2027-06-20 | Sun | v3.1.0
2027-06-21 | Mon | v3.1.0
2027-06-22 | Tue | v3.1.0
2027-06-23 | Wed | v3.1.0
2027-06-24 | Thu | v3.1.0
2027-06-25 | Fri | v3.1.0
2027-06-26 | Sat | v3.1.0
2027-06-27 | Sun | v3.1.0
2027-06-28 | Mon | v3.1.0
2027-06-29 | Tue | v3.1.0
2027-06-30 | Wed | v3.1.0
2027-07-01 | Thu | v3.1.0
2027-07-02 | Fri | v3.1.0
2027-07-03 | Sat | v3.1.0
2027-07-04 | Sun | v3.1.0
2027-07-05 | Mon | v3.1.0
2027-07-06 | Tue | v3.1.0
2027-07-07 | Wed | v3.1.0
2027-07-08 | Thu | v3.1.0
2027-07-09 | Fri | v3.1.0
2027-07-10 | Sat | v3.1.0
2027-07-11 | Sun | v3.1.0
2027-07-12 | Mon | v3.1.0
2027-07-13 | Tue | v3.1.0
2027-07-14 | Wed | v3.1.0
2027-07-15 | Thu | v3.1.0
2027-07-16 | Fri | v4.0.0
2027-07-17 | Sat | v4.0.0
2027-07-18 | Sun | v4.0.0
2027-07-19 | Mon | v4.0.0
2027-07-20 | Tue | v4.0.0
2027-07-21 | Wed | v4.0.0
2027-07-22 | Thu | v4.0.0
2027-07-23 | Fri | v4.0.0
2027-07-24 | Sat | v4.0.0
2027-07-25 | Sun | v4.0.0
2027-07-26 | Mon | v4.0.0
2027-07-27 | Tue | v4.0.0
2027-07-28 | Wed | v4.0.0
2027-07-29 | Thu | v4.0.0
2027-07-30 | Fri | v4.0.0
2027-07-31 | Sat | v4.0.0
2027-08-01 | Sun | v4.0.0
2027-08-02 | Mon | v4.0.0
2027-08-03 | Tue | v4.0.0
2027-08-04 | Wed | v4.0.0
2027-08-05 | Thu | v4.0.0
2027-08-06 | Fri | v4.0.0
2027-08-07 | Sat | v4.0.0
2027-08-08 | Sun | v4.0.0
2027-08-09 | Mon | v4.0.0
2027-08-10 | Tue | v4.0.0
2027-08-11 | Wed | v4.0.0
2027-08-12 | Thu | v4.0.0
2027-08-13 | Fri | v4.0.0
2027-08-14 | Sat | v4.0.0
2027-08-15 | Sun | v4.0.0
2027-08-16 | Mon | v4.1.0
2027-08-17 | Tue | v4.1.0
2027-08-18 | Wed | v4.1.0
2027-08-19 | Thu | v4.1.0
2027-08-20 | Fri | v4.1.0
2027-08-21 | Sat | v4.1.0
2027-08-22 | Sun | v4.1.0
2027-08-23 | Mon | v4.1.0
2027-08-24 | Tue | v4.1.0
2027-08-25 | Wed | v4.1.0
2027-08-26 | Thu | v4.1.0
2027-08-27 | Fri | v4.1.0
2027-08-28 | Sat | v4.1.0
2027-08-29 | Sun | v4.1.0
2027-08-30 | Mon | v4.1.0
2027-08-31 | Tue | v4.1.0
2027-09-01 | Wed | v4.1.0
2027-09-02 | Thu | v4.1.0
2027-09-03 | Fri | v4.1.0
2027-09-04 | Sat | v4.1.0
2027-09-05 | Sun | v4.1.0
2027-09-06 | Mon | v4.1.0
2027-09-07 | Tue | v4.1.0
2027-09-08 | Wed | v4.1.0
2027-09-09 | Thu | v4.1.0
2027-09-10 | Fri | v4.1.0
2027-09-11 | Sat | v4.1.0
2027-09-12 | Sun | v4.1.0
2027-09-13 | Mon | v4.1.0
2027-09-14 | Tue | v4.1.0
2027-09-15 | Wed | v4.1.0
2027-09-16 | Thu | v5.0.0
2027-09-17 | Fri | v5.0.0
2027-09-18 | Sat | v5.0.0
2027-09-19 | Sun | v5.0.0
2027-09-20 | Mon | v5.0.0
2027-09-21 | Tue | v5.0.0
2027-09-22 | Wed | v5.0.0
2027-09-23 | Thu | v5.0.0
2027-09-24 | Fri | v5.0.0
2027-09-25 | Sat | v5.0.0
2027-09-26 | Sun | v5.0.0
2027-09-27 | Mon | v5.0.0
2027-09-28 | Tue | v5.0.0
2027-09-29 | Wed | v5.0.0
2027-09-30 | Thu | v5.0.0
2027-10-01 | Fri | v5.0.0
2027-10-02 | Sat | v5.0.0
2027-10-03 | Sun | v5.0.0
2027-10-04 | Mon | v5.0.0
2027-10-05 | Tue | v5.0.0
2027-10-06 | Wed | v5.0.0
2027-10-07 | Thu | v5.0.0
2027-10-08 | Fri | v5.0.0
2027-10-09 | Sat | v5.0.0
2027-10-10 | Sun | v5.0.0
2027-10-11 | Mon | v5.0.0
2027-10-12 | Tue | v5.0.0
2027-10-13 | Wed | v5.0.0
2027-10-14 | Thu | v5.0.0
2027-10-15 | Fri | v5.0.0

## Weeks
Week starting (Mon) | Week ending | Planned h | Logged h | Gap
2026-10-12 | 2026-10-18 | 31.5 | 0 | -31.5
2026-10-19 | 2026-10-25 | 31.5 | 0 | -31.5
2026-10-26 | 2026-11-01 | 31.5 | 0 | -31.5
2026-11-02 | 2026-11-08 | 31.5 | 0 | -31.5
2026-11-09 | 2026-11-15 | 31.5 | 0 | -31.5
2026-11-16 | 2026-11-22 | 31.5 | 0 | -31.5
2026-11-23 | 2026-11-29 | 31.5 | 0 | -31.5
2026-11-30 | 2026-12-06 | 31.5 | 0 | -31.5
2026-12-07 | 2026-12-13 | 31.5 | 0 | -31.5
2026-12-14 | 2026-12-20 | 31.5 | 0 | -31.5
2026-12-21 | 2026-12-27 | 31.5 | 0 | -31.5
2026-12-28 | 2027-01-03 | 31.5 | 0 | -31.5
2027-01-04 | 2027-01-10 | 31.5 | 0 | -31.5
2027-01-11 | 2027-01-17 | 31.5 | 0 | -31.5
2027-01-18 | 2027-01-24 | 31.5 | 0 | -31.5
2027-01-25 | 2027-01-31 | 31.5 | 0 | -31.5
2027-02-01 | 2027-02-07 | 31.5 | 0 | -31.5
2027-02-08 | 2027-02-14 | 31.5 | 0 | -31.5
2027-02-15 | 2027-02-21 | 31.5 | 0 | -31.5
2027-02-22 | 2027-02-28 | 31.5 | 0 | -31.5
2027-03-01 | 2027-03-07 | 31.5 | 0 | -31.5
2027-03-08 | 2027-03-14 | 31.5 | 0 | -31.5
2027-03-15 | 2027-03-21 | 31.5 | 0 | -31.5
2027-03-22 | 2027-03-28 | 31.5 | 0 | -31.5
2027-03-29 | 2027-04-04 | 31.5 | 0 | -31.5
2027-04-05 | 2027-04-11 | 31.5 | 0 | -31.5
2027-04-12 | 2027-04-18 | 31.5 | 0 | -31.5
2027-04-19 | 2027-04-25 | 31.5 | 0 | -31.5
2027-04-26 | 2027-05-02 | 31.5 | 0 | -31.5
2027-05-03 | 2027-05-09 | 31.5 | 0 | -31.5
2027-05-10 | 2027-05-16 | 31.5 | 0 | -31.5
2027-05-17 | 2027-05-23 | 31.5 | 0 | -31.5
2027-05-24 | 2027-05-30 | 31.5 | 0 | -31.5
2027-05-31 | 2027-06-06 | 31.5 | 0 | -31.5
2027-06-07 | 2027-06-13 | 31.5 | 0 | -31.5
2027-06-14 | 2027-06-20 | 31.5 | 0 | -31.5
2027-06-21 | 2027-06-27 | 31.5 | 0 | -31.5
2027-06-28 | 2027-07-04 | 31.5 | 0 | -31.5
2027-07-05 | 2027-07-11 | 31.5 | 0 | -31.5
2027-07-12 | 2027-07-18 | 31.5 | 0 | -31.5
2027-07-19 | 2027-07-25 | 31.5 | 0 | -31.5
2027-07-26 | 2027-08-01 | 31.5 | 0 | -31.5
2027-08-02 | 2027-08-08 | 31.5 | 0 | -31.5
2027-08-09 | 2027-08-15 | 31.5 | 0 | -31.5
2027-08-16 | 2027-08-22 | 31.5 | 0 | -31.5
2027-08-23 | 2027-08-29 | 31.5 | 0 | -31.5
2027-08-30 | 2027-09-05 | 31.5 | 0 | -31.5
2027-09-06 | 2027-09-12 | 31.5 | 0 | -31.5
2027-09-13 | 2027-09-19 | 31.5 | 0 | -31.5
2027-09-20 | 2027-09-26 | 31.5 | 0 | -31.5
2027-09-27 | 2027-10-03 | 31.5 | 0 | -31.5
2027-10-04 | 2027-10-10 | 31.5 | 0 | -31.5
2027-10-11 | 2027-10-17 | 31.5 | 0 | -31.5
Formulas:
Week ending = [Week starting (Mon)]+6